Nishna Productions, Inc.

Strategic Plan Reporting

Developed 10/27/2025

Goal 1: Formalize a Fund Development Plan				Team Members: Emily, Brenton, Monica, Rusty

Short Term Goal:  Build donor relationships, and enhance the grant writing process

Obstacles/Hurdles:

Will involve other people

Lack of knowledge regarding how to build a development plan

Intimidating task

Lack of donor knowledge about Nishna Productions, Inc.

Next Steps:

Explore related educational opportunities

Identify potential donors

Identify grant sources

| Action Steps | Time Frame | Responsible | Status |
| --- | --- | --- | --- |
| - Reach out to local partners for ideas or resources to utilize to search for grant opportunities. This may be software/websites, grant writers, etc. | 6/30/2026 | Rusty, Monica, Emily |  |
| - Explore opportunities for grant writing courses/workshops. | 5/1/2026 | Emily |  |
| - Explore establishing an endowment for NPI. Get educated on how endowments work to be able to explain to potential donors. | 5/31/2026 6/30/2025 | Monica & Rusty Monica, Emily, & Brenton |  |
| - Explore the ability to use AI to perform grant writing. | 5/1/2026 | Emily |  |
| - Contact partners in the community to begin to build a list of potential donors. Start with existing donor list. | 6/30/2026 & Ongoing | Monica, Rusty, Emily, & Brenton |  |
| - Develop a marketing strategy to approach donors with. Need to sell the benefits of supporting NPI on an on-going basis. | 7/30/2026 & Ongoing | Monica, Rusty, Emily, & Brenton |  |

Goal 2: Build a Leadership Development Program			Team Members: Monica, Jennifer, Lisa, Cheryl, Rachael, Brenton

Short Term Goal:  Identify potential candidates, build skill assessment, and outline of curriculum.

Obstacles/Hurdles:

Staff buy-in

Gatekeeping by supervisors

Staff fear/lack of self-confidence

Cost – time & money

Next Steps:

Shadow other organizations

Conduct a self-assessment

Identify potential candidates

| Action Steps | Time Frame | Responsible | Status |
| --- | --- | --- | --- |
| - Reach out to other organizations to see if any have developed a program that we could use as an example to develop best practices. | 4/1/26 | Monica & Brenton |  |
| - Assess the needs for this program – what is driving the need to develop this training program for our staff, what are the goals for the program? | 4/30/26 | Committee |  |
| - Develop the curriculum for the program. | 7/31/26 | Committee |  |
| - Market the program to staff. | 6/30/26 & Ongoing | Committee, Development Specialist, Supervisory Staff |  |
| - Identify candidates to participate in the program. | 7/31/26 | Committee |  |

Goal 3: Active Real Estate/Site Planning Committee			Team Members: Brenton, Mary W., Rachael, Doug, Rusty, Monica, 														    Jennifer F., Ziada

Short Term Goal:  Define needs – “Where do we want to go.”

Obstacles/Hurdles:

Community acceptance

Availability of properties

Cost associated

Ability to identify properties without pushback from city/neighbors

Next Steps:

Build a list of opportunities

Perform a needs assessment based on current and future activities.

| Action Steps | Time Frame | Responsible | Status |
| --- | --- | --- | --- |

Goal 4: Intentional Recruitment/Retention Program			Team Members: Emily, Jennifer, Monica, Brenton, Lisa, Cheryl,

Rachael

Short Term Goal:  Determine why people leave.  Develop the story

Obstacles/Hurdles:

Compensation levels

Competition for employees

Schedules

Current Culture

Next Steps:

Refine exit interview process

Develop a specific marketing strategy

Exit Interview Process:

| Action Steps | Time Frame | Responsible | Status |
| --- | --- | --- | --- |
| - Revise Questions on the Exit Interview form. | 4/1/2026 | HR Manager | 3/10 – Completed |
| - Change the process for completion – Human Resources will now be completing the interview with the employee, either in person or over the phone. | Immediate & On-going | HR Manager | 3/15 – This is now completed. HR Manager will continue with this change. |
| - Human Resources will track data to determine reasons for voluntary terminations. - Create a tracking mechanism. - Define Categories to be tracked, both Positives and Negatives. - Provide data for status reports - Add to Quality Indicators to encourage system improvement. - Discuss data gathered at Team Leader Roundtable events. | 4/1/2026 On-going 7/1/2026 7/1/2026 & On-going | HR Manager Team Members HR Manager HR Manager | 3/30 – HR Manager has created a tracking document. She will track data and provide information for reporting purposes. |

Marketing Strategy:

| Action Steps | Time Frame | Responsible | Status |
| --- | --- | --- | --- |
| - Meet on a weekly basis to develop HR posts for recruitment on Facebook. | On-going | HR Manager & Development Specialist |  |
| - Look at rebranding for the organization – review mission, vision, motto, & logo. Propose changes for approval. | 6/1/2026 | Marketing Committee |  |
| - Work on outreach to local schools. We will work to develop opportunities to educate students about what we do at NPI. | 4/1/2026 & On-going | Development Specialist, Marketing Committee |  |
| - Develop an Internal Marketing Strategy to market to existing staff. - Development Specialist – team building at member services meetings. - Bi-weekly emails/communication from leadership – what’s happening at NPI? - Engagement Committee activities. - Leadership Development Program activities. - Implement in the general orientation process. | On-going | Development Specialist Marketing Committee Engagement Committee Administrative Team |  |

Goal 5: Develop Asset Management Program			Team Members: Monica, Brenton, Mike, Bill, Mary W. Lisa, Cheryl, Kelly

Short Term Goal:  Prioritize/update the existing needs assessment, develop a cost plan, preventative maintenance schedule, fleet management program

Obstacles/Hurdles:

Overwhelming list

Cost

Not enough maintenance staff with specialized knowledge

Next Steps:

Complete prioritization process

Assess staff skills/needs. Determine if need to contract out some portions of the work.

Develop a budget for high priority items

| Action Steps | Time Frame | Responsible | Status |
| --- | --- | --- | --- |

Goal 6:  Community Engagement Plan			Team Members: Emily, Jennifer F., Jennifer G., Deb T., Barb K., 														   (eventually Monica & Board of Directors)

Short Term Goal:  Develop the story, identify opportunities to increase engagement

Obstacles/Hurdles:

Staff buy-in

Next Steps:

Develop and publish story

Identify people who can be the voice of Nishna Productions, Inc.

| Action Steps | Time Frame | Responsible | Status |
| --- | --- | --- | --- |

Goal 7: Develop an IT Plan							Team Members: Brenton, Monica, Platinum, Shelly, Rachael, Ziada

Short Term Goal:  Device replacement plan, vision plan – what are the future needs and opportunities for IT

Obstacles/Hurdles:

Cost

Rate of change

The need for a great deal of galvanizing

Next Steps:

Assess current assets, what we are using and build a replacement plan

Increase knowledge of what is possible

| Action Steps | Time Frame | Responsible | Status |
| --- | --- | --- | --- |

Goal 8: Board Development Plan						Team Members: Monica, members of Board of Directors

Short Term Goal:  Develop a “hit list” of potential board members, begin seed planting conversations.

Obstacles/Hurdles:

Excuse of “I don’t have time.”

Lack of regular openings on the board

Next Steps:

Add board development as an agenda item for board meeting

Engage the current board members in the process of building a list of prospective board members

| Action Steps | Time Frame | Responsible | Status |
| --- | --- | --- | --- |
| - Initial discussion with the Board of Directors | 3/23/26 | Executive Director | 3/23/26: There was initial discussion with the Board of Directors at the monthly meeting. Board members suggested that it be an ongoing agenda item to keep in front of the board as a reminder to be recruiting and thinking about potential members. This will be added to every board agenda as an additional item for discussion. |
| - Work on a list of potential members for recruitment to serve on the board that represent all counties in the service area. | On-going | Executive Director, Board of Directors |  |